## Proj. Cost Sch. (DAC to manage)
Revised 09-21-21
NOTE: Per 9-1-20 discussion with County, the Library contributions pre-bond ($483k) have been removed.
COSTS | [5 empty] | Budget | Notes | Responsibility | Notes
1 | Construction Costs
1.1 | Construction Contract - Dick Anderson Construction (Original GMP = 28,000,774.49) |  |  |  |  | 28000774.49 | Original GMP | DAC
1.2 | Change Orders (Paid by Construction Contingency, Owner Contingency, and/or added Revenue) |  |  |  |  | 782680.34 | Through CO 16 | DAC
| Owner Contingency Funded Items |  | 556843.64
| Foundation Funded Items |  | 225836.7
[5 empty] | Subtotal | 28783454.83 | Current GMP (8-25-21) | DAC
| Current Construction Contingency - Included in 1.1 - (Original $274,490) |  |  |  |  | 0 | Value in 1.1
2 | Professional Services
2.1 | CM at Risk, CM fee - Dick Anderson Construction (Pre-Construction not in 1.1) |  |  |  |  | 45000 | Contract - DAC | DAC | Confirmed on 03.02.2017, this is only their preconstruction fee
2.2 | Pre-Bond Architectural and Engineering Fee - A&E |  |  |  |  | 0 | Zeroed on 9-1-20
2.3 | Post Bond / Pre Design Reprogramming Effort after Bond Fee - A&E |  |  |  |  | 0 | Zeroed on 9-1-20
2.4 | Design Contract - Architectural and Engineering Fee (Schematic Design through Construction) - A&E |  |  |  |  | 2720090 | Contract - A&E
2.41 | Design Contract Amendment 1 - (Large Well Design & A/V Consultant) - A&E |  |  |  |  | 32000 | Contract - A&E
2.42 | Design Contract Amendment 2 - (Remove GeoTech & Add Reimbursable Expenses) - A&E |  |  |  |  | 11000 | Contract - A&E
2.43 | Design Contract Amendment 3 - (Additional CA thru August 2020) - A&E |  |  |  |  | 170968.36 | Contract - A&E
2.44 | Design Contract Amendment 4 - (Contract Extension Sept 2021 / True-up) - A&E |  |  |  |  | 248000 | Contract - A&E
[5 empty] | Subtotal | 3227058.36 |  |  | Not Including Library reimbursement indicated above
3 | Development and Soft Costs
3.1 | Design Contingency | 0% |  |  |  | - | Zeroed at Construction | A&E - MSR | Over course of the project will go to 0%
3.2 | Cost of Demolition |  |  |  |  | in 1.1 | Final | A&E - MSR | need to verify if this is for just the Payne Block or for the Library site as well
3.3 | Rent to Terry Payne (35 Months @ $28k/MO = May 2017 through March 2020) - See Updated Contract Limiting Rent to March 31 |  |  |  |  | 980000 | Final | MPL | $8/sf (from Payne), for approximately 2.5 years; current Library SF = 42,000
3.31 | Heat & Cover plus snow removal - Winter Conditions |  |  |  |  | in 1.1 | Final | DAC | Marty Will adjust his Estimate to accommodate winter heat
3.4 | Issuance of Bonds | [6 empty] | County | Bonds
3.41 | Issuance of Bonds - Series 1 |  |  |  |  | 88850 | Final | County | 1st Issuance
3.42 | Issuance of Bonds - Series 2 |  |  |  |  | 228778.88 | Final | County | 2nd Issuance
3.5 | Building Permits (new and demo) |  |  |  |  | in 1.1 | Final |  | Included in Construction Cost - confirmed on 03.02.2017
3.6 | Printing Costs |  |  |  |  | 5000 | T&M Allowance
3.7 | Relocation Expenses |  |  |  |  | 30000 | Estimate | MPL | estimated moving costs into new facility
3.8 | Rezoning Fee |  |  |  |  | 9930 | Final | A&E - MSR | Rezone both blocks
3.9 | Site Survey |  |  |  |  | in 1.1 | Final | A&E - MSR | In Fee Proposal
3.1 | Geotechnical Report |  |  |  |  | in 2.2 | Final |  | A&E Fee's
3.11 | Independent Construction Materials Testing |  |  |  |  | 92000 | Budget | Library | Bid From Tetra Tech
3.12 | Appraisal |  |  |  |  | 7500 | Final | A&E - MSR | Kemble Kosena
3.13 | Asbestos Sampling |  |  |  |  | 13250 | Final | A&E - MSR | Northern Industrial Hygiene
3.14 | Phase 1 Environmental Survey |  |  |  |  | 5860 | Final | A&E - MSR | NewFields
3.15 | LEED certification administration fees |  |  |  |  | - | Not Accepted | A&E - MSR | LEED not being pursued
3.16 | LEED certification |  |  |  |  | - | Not Accepted | A&E | N/A
3.17 | Building Commissioning Services |  |  |  |  | in 1.1 | Final |  | In Final Fees to Library
3.18 | Fundraising / CC |  |  |  |  | - |  |  | Foundation (CC) - provides cost of fundraising
3.19 | Design Charrette (Branding) |  |  |  |  | 0 | Zeroed on 9-1-20
3.2 | Fencing For Property |  |  |  |  | 0 | Zeroed on 9-1-20
3.21 | Asbestos Abatement |  |  |  |  | 0 | Zeroed on 9-1-20
3.22 | Historical Removal - Documentation |  |  |  |  | 0 | Zeroed on 9-1-20
[5 empty] | Subtotal | 1461168.88
4 | Furniture Fixtures and Equipment
4.1A | Furnishings - Library (Original = $2,011,595 / Revised Estimate / Savings moved to Owner Contingency) |  |  |  |  | 1921202.74 | Final, update 6-25-20 | A&E - MSR | furniture budget including contingency 02.20.18
4.1B | Furnishings - Partners (Original 452,405 / Reduced Scope) |  |  |  |  | 197572 | Final, update 6-25-20
4.2 | Interior Signage (Includes $25k allowance for Donor Wall) |  |  |  |  | 101855 | Final, update 6-25-20 | A&E - MSR
4.3 | Equipment |  |  |  |  | 119000 | Estimate, update 2-3-20 | MPL | Copiers, printers, printing press, etc. MPL TO CONFIRM
4.4 | Computer, Phones and Networking Equipment |  |  |  |  | 188000 | Estimate, update 2-3-20 | MPL | MPL to confirm
4.5 | Automated Materials Handling (Includes Security Book Systems) |  |  |  |  | 550000 | Final | MPL | Lyngsoe book handling Provided by MPL- 6.8.18 Cost Shown at $530K What level of Confidence do we have?
4.6 | Building Security Systems |  |  |  |  | 134326.66 | Final, update 9-23-20 | MPL | $3.41 / sqft
4.7 | A/V Systems - (CO + $13,326.66 on 9-23-20) |  |  |  |  | 297000 | Final | MPL | $1.70 / sqft $350K EQUIPMENT LIST NEEDS TO BE BROKEN INTO PARTNER QUANTITIES
4.8 | Art |  |  |  |  | - |  | MPL | MPL to confirm, MMAC?
4.11 | Kitchen Equipment |  |  |  |  | - | Moved to 4.2 | MPL
4.12 | Opening Day Collection Fund |  |  |  |  | 400000 | Final | MPL | covered in separate budget
4.13 | Partner Exhibits |  |  |  |  | not included
4.14 | Miscellaneous Expenditures 1 (after February 2021 - See Expenditures ) |  |  |  |  | 67697.22 | Added 8-26-21 |  | by partners
4.15 | Miscellaneous Expenditures 2 (Big Bear Signs, Smith Grading, Systems NW, & Litigation Abstracts) |  |  |  |  | 21853.35 | Added 9-21-21
4.16 | Expenditures 3 (Playtime, Tri-Couinties, Solar Plexus, Litigation Absract, Inc. & Sign Solutions) |  |  |  |  | 188093.06 | Added 10-19-21
[5 empty] | Subtotal | 4186600.03
COST SUMMARY TOTALS
1 | Construction Costs |  |  |  |  | 28783454.83
2 | Professional Services |  |  |  |  | 3227058.36
3 | Development and Soft Costs |  |  |  |  | 1461168.88
4 | Furniture Fixtures and Equipment |  |  |  |  | 4186600.03
[5 empty] | Subtotal | 37658282.1
| Owner's Contingency - Current (Original $363,178.19) |  |  |  |  | 37493.35 |  |  | Reduced from 2.8% (958K) to 1% 02.20.18
[5 empty] | TOTAL ESTIMATED PROJECT COST | 37695775.45
REVENUE
| Bond Proceeds |  |  |  |  | 30327667 | Updated 2-3-20
Library Contribution
|  |  |  | Architectural Engineering Fees | 0 | Zeroed on 9-1-20
|  |  |  | Design Charrette (Branding) | 0 | Zeroed on 9-1-20
|  |  |  | Fencing For Property | 0 | Zeroed on 9-1-20
|  |  |  | Asbestos Abatement | 0 | Zeroed on 9-1-20
|  |  |  | Historical Removal - Documentation | 0 | Zeroed on 9-1-20
|  |  |  | Added MPL Contributions | 188093.06 | Added 10-19-21
[5 empty] | Subtotal | 188093.06
| Partners Contribution (Furniture Purchases) |  |  |  |  | 197572 | Updated, 2-3-20
Foundation Contribution
|  |  |  | Transfer of FIB CDs/interest | 1293004
|  |  |  | Transfer of FIB CDs/interest | 1532810
|  |  |  | Initial Cash Transfer (July 2018) | 800000
|  |  |  | 2nd Cash Transfer (December 2018) | 138443
|  |  |  | 3rd Cash Transfer (July 2019) | 310000
|  |  |  | 4th Cash Transfer (July 2020) | 1100000
|  |  |  | Line of Credit (July 2018; Reduced July 2019, July 2020) | 908871
[5 empty] | Subtotal | 6083128
| Actual Interest Earnings on Bonds & Cash - 12-31-2019 |  |  |  |  | 899315.39 | Updated 2-19-21
[5 empty] | TOTAL REVENUE | 37695775.45
[5 empty] | OVER / UNDER BUDGET | #REF!
| Owner Contingency Breakdown | 363178.19 |  | Original
Construction Contract Adjustments - See 1.2
| DAC Change Order 1 (PCO 2, & 6) |  | -69030.59
| DAC Change Order 2 (PCO 3R2) | -35656.4
| DAC Change Order 3 (PCO 9 & 10) | -24142.99
| DAC Change Order 4 (PCO 12) |  | -2630.41
| DAC Change Order 5 (PCOs 20, 22, 23, 25, & 26) |  | -29637.36
| DAC Change Order 6 (PCOs 31.1, 34, 36, & 37) |  | -49531.27
| DAC Change Order 7 (PCO 42, 43, 44) |  | -40290.09
| DAC Change Order 8 (PCO 38R1, 45, 47, & 49) |  | -57072.74
| DAC Change Order 9 (PCO 51, 53, 54) |  | -26616.95
| DAC Change Order 10 (PCO 59, 60, 61, 62R1, 63, 64, 65, 66, 67, 68, 69, 70, 71, 72) |  | -46735.21
| DAC Change Order 11 (PCO 76, 77R1, 79) |  | -50000.32
| DAC Change Order 12 (PCOs 82, 83, 84R1, & 85) |  | -29407.33
| DAC Change Order 13 (PCOs 86, 87R1, 88, 91, 92, & 93) |  | -28223.45
| DAC Change Order 14 (PCOs 95, 96, 97, 98, 99, & 100) |  | -14420.35
| DAC Change Order 15 (PCOs 104. 105. 106. 107. 108, 109, 110, & 111) |  | -47404.63
| DAC Change Order 16 (PCO 112) |  | -6043.55
| Subtotal | -556843.64
Other Adjustments
| Foundation Overfunding for DAC CO#2 |  | 2606.3 | Foundation funded $90,000 cost was $87,393.70
| Estimated Furniture Budget Savings (4.1A) |  | 88354 | Updated Estimate 1-28-20
| Final Budget Savings - 4.1 Furnishings |  | 2038.26 | 6-25-20 Adjustment
| Final Budget Savings - 4.2 Signage |  | 55145 | 6-25-20 Adjustment
| Subtotal | 148143.56
-704987.2
| Current Owner Contingency Budget | 49287.37
| Correction to Balance Cost & Revenue | -11794.02 |  | 0
| Revised Owner Contingency Budget | 37493.35 |  | Value used on Cost Sheet
Added Foundation Funded Items - See 1.2
| DAC Change Order 1 - (PCO 5 - Sky fold Door) |  | 138443 | See 1.2 & Foundation Contribution
| DAC Change Order 2 - (PCO 8 - Maker Space & Classroom Casework) |  | 87393.7 | See 1.2 & Foundation Contribution / See Contingency Breakdown
| Total | 225836.7